Design that Defines. Impact that Endures.

PURSUIT & CONTRACTING — RFP-RELATED COMMUNICATIONS

Oakhaven Public Safety Campus

Internal and external correspondence available at the pursuit / contracting stage

| Project | Oakhaven Public Safety Campus (Pursuit No. GRC-P-26-0142) |
| --- | --- |
| Owner / Solicitation | City of Oakhaven, Louisiana — RFP No. OEP-2026-004 |
| Pursuit Manager | Elena Cross, Marketing Director |
| Pursuit Lead (PIC) | Marcus Webb, AIA, Principal |
| Period covered | May 18 – July 28, 2026 (RFP issue → award & handoff) |

Purpose.  A consolidated record of the communications a firm accumulates during pursuit — from receiving the RFP, through the Go/No-Go decision, clarification questions, proposal submission, selection, and the pursuit-to-PM handoff. This is the correspondence that exists before the project is truly 'live.' This is a summary log, not the full correspondence trail — pursuit-stage communications moved by email and the RFP portal.

# 1.  Communications Log

| Date | Type | From → To | Subject |
| --- | --- | --- | --- |
| May 18, 2026 | External · in | City of Oakhaven → Grace (BD) | RFP OEP-2026-004 issued — invitation to propose |
| May 20, 2026 | Internal | E. Cross → Pursuit team | Go/No-Go decision — Oakhaven Public Safety Campus (GO) |
| May 21, 2026 | External · out | Grace → T. Nguyen (City) | Notice of intent to respond; respondent registration |
| May 26, 2026 | Internal | M. Webb → Pursuit team | Pursuit team, fee strategy & Target Multiplier |
| Jun 3, 2026 | External · out | Grace → T. Nguyen (City) | Clarification questions (before Jun 5 deadline) |
| Jun 9, 2026 | External · in | City → all respondents | Addendum No. 1 — answers to questions |
| Jun 17, 2026 | Internal | D. Reyes / M. Webb | Proposal & fee review; approval to submit |
| Jun 19, 2026 | External · out | Grace → K. Whitfield (City) | Proposal transmittal — Oakhaven Public Safety Campus |
| Jun 30, 2026 | External · in | City → Grace | Shortlist — finalist interview invitation |
| Jul 13, 2026 | External · in | City → Grace | Notice of selection / intent to award |
| Jul 27, 2026 | External · both | City ↔ Grace | Owner/Architect Agreement executed; Notice to Proceed |
| Jul 28, 2026 | Internal | E. Cross → D. Reyes | Pursuit-to-PM handoff — brief, assumptions, pricing |

The full text of the key items follows. Routine acknowledgements are logged above only.

# 2.  Key Communications (full text)

## 2.1  Internal — Go/No-Go Decision (May 20, 2026)

| From | Elena Cross, Marketing Director |
| --- | --- |
| To | Marcus Webb (PIC); Dana Reyes (PM-designate); Finance; Pursuit team |
| Date | May 20, 2026 |
| Subject | Go/No-Go — Oakhaven Public Safety Campus (RFP OEP-2026-004) |

Team — we screened the Oakhaven RFP against the Go/No-Go criteria this morning. Recommendation: GO.

Fit is strong: a Risk Category IV civic/public-safety project in our core market, a client type we know, and a scope centered on architecture and interiors with engineering we can carry. Civil is Owner-retained, which removes our highest-variability sub. Schedule is achievable and the fee basis supports a healthy margin.

Watch-items carried into the proposal: Owner-furnished dispatch/CAD systems (coordination risk), long-lead generator, and the hardened-core scope. See the completed Go/No-Go Form for scores.

Next: I'll register us as a respondent and route clarification questions before the June 5 deadline. Marcus to set the pursuit strategy and fee development.

## 2.2  External — Clarification Questions to the Owner (June 3, 2026)

| From | Grace Design Studios (E. Cross) |
| --- | --- |
| To | Thomas Nguyen, Purchasing Agent, City of Oakhaven |
| Date | June 3, 2026 |
| Subject | RFP OEP-2026-004 — Respondent questions |

Mr. Nguyen — thank you for the opportunity. Please consider the following clarification questions:

- Q1.  Will the boundary/topographic survey and geotechnical report be Owner-furnished, and when would they be available to the selected firm?

- Q2.  Please confirm that civil / site engineering is contracted directly by the City, and describe the coordination the City expects from the A/E.

- Q3.  Please confirm the 911 dispatch console furniture and CAD/radio systems are Owner-Furnished (OFCI), and whether a systems vendor has been selected.

- Q4.  Does the $40,000,000 construction budget include site/civil work and Owner-furnished equipment, or is it the building construction contract only?

- Q5.  Please confirm required professional liability limits and any modifications to AIA B101-2017 the City intends.

## 2.3  External — Owner Addendum No. 1: Answers (June 9, 2026)

| From |  | City of Oakhaven — Office of Emergency Preparedness |
| --- | --- | --- |
| To |  | All registered respondents |
| Date |  | June 9, 2026 |
| Subject |  | Addendum No. 1 — responses to respondent questions |
| # | Answer |  |
| A1 | The survey and geotechnical report will be Owner-furnished and available at Notice to Proceed. |  |
| A2 | Civil / site engineering is retained directly by the City under a separate contract. The A/E coordinates with the City's civil engineer but does not provide civil design. |  |
| A3 | Dispatch console furniture and the CAD/radio systems are Owner-Furnished, Contractor-Installed. Vendor selection is in progress; the A/E coordinates supporting infrastructure. |  |
| A4 | The $40M construction budget is the building construction contract (site work by the GC). It excludes A/E fees, the Owner's civil contract, and Owner-furnished equipment. |  |
| A5 | Professional liability of $5,000,000 per claim / $5,000,000 aggregate. Agreement is AIA B101-2017 as modified per the RFP. |  |

## 2.4  Internal — Fee Strategy & Target Multiplier (May 26, 2026)

| From | Marcus Webb, Principal-in-Charge |
| --- | --- |
| To | Pursuit team; Finance; Dana Reyes |
| Date | May 26, 2026 |
| Subject | Fee strategy & Target Multiplier — Oakhaven |

Total design fee target: $2,800,000 (≈7% of the $40M construction cost). Grace's Net Service Fee is $1,400,000 for architecture & interiors; subconsultants carried at $1,400,000; civil excluded.

## 2.5  External — Proposal Transmittal (June 19, 2026)

| From | Grace Design Studios (E. Cross) |
| --- | --- |
| To | Karen Whitfield, Director of Emergency Preparedness, City of Oakhaven |
| Date | June 19, 2026 |
| Subject | Proposal — Oakhaven Public Safety Campus (RFP OEP-2026-004) |

Ms. Whitfield — please find enclosed Grace Design Studios' proposal for architectural and engineering design services for the Oakhaven Public Safety Campus, submitted in response to RFP OEP-2026-004 and incorporating Addendum No. 1.

Our fee proposal and full scope of services are enclosed, per Addendum No. 1. We would be honored to serve the City on this essential facility. We welcome any questions.

## 2.6  External — Notice of Selection (July 13, 2026)

| From | City of Oakhaven — Office of Emergency Preparedness |
| --- | --- |
| To | Grace Design Studios |
| Date | July 13, 2026 |
| Subject | Notice of Selection / Intent to Award — RFP OEP-2026-004 |

The City of Oakhaven selection committee has identified Grace Design Studios as the top-ranked respondent for the Oakhaven Public Safety Campus. The City intends to enter into an Owner/Architect Agreement (AIA B101-2017, as modified). We will forward the agreement for execution; anticipated Notice to Proceed is July 27, 2026.

## 2.7  Internal — Pursuit-to-PM Handoff (July 28, 2026)

| From | Elena Cross, Marketing Director |
| --- | --- |
| To | Dana Reyes, Project Manager |
| Date | July 28, 2026 |
| Subject | Oakhaven: what was promised, assumed, and priced |

Dana — the project is yours. Summary for your handoff notes:

Promised: full A/E design for the 55,000-GSF Risk Cat IV campus; civil coordination only.

Assumed: survey & geotech Owner-furnished at NTP; dispatch/CAD systems OFCI; one Owner review cycle per phase gate.

Priced: $2.8M total design fee ($1.4M Grace net),

At risk: Owner-furnished dispatch specs timing, long-lead generator, hardened-core coordination.

The executed agreement, the proposal, the Go/No-Go Form, and the Project Budget Spreadsheet are in the pursuit file. Kickoff is Aug 10. Come find me for anything that didn't make it into writing.