## Budget Updated
Budget
Oakhaven Public Safety Campus - GRC-26-0142
[8 empty] | Updated: | 2026-07-30 | CK
Fee based on a Construction Cost of: | [5 empty] | 40000000 | 7% |  | 2800000 | Or if lump sum, input the fee
Projected Engineering Fees | [6 empty] | 50% |  | 1400000 | If fees are known, they go here and can be totaled below in the consultant area
Architectural / Interior Design Fees | [6 empty] | 50% |  | 1400000
Fee Less % Profit | 20%
PROJECT SUMMARY (NOTE:FEES AND COST SHOWN DO NOT INCLUDE ENGINEERING) | [10 empty] | FEE BREAKDOWN |  |  | CONSULTANT FEES | Beam & Assoc. | Fielding Eng. | Fielding Eng. | By Owner (excl.) | firm name | Sentinel Tech. | Harmonic Acou. | firm name | firm name | firm name | firm name | firm name | firm name | firm name | Expenses
|  | phase start | phase finish | # of days |  | COST | FEE | PROFIT | GRACE FEE % |  | Total Fee | Consultants | GRACE |  | Structural | Mech/Plumb | Elec | Civil | Landscape | Tech/Security | Acoustical | Discipline | Discipline | Discipline | Discipline | Discipline | Discipline | Discipline | (Printing/Mileage/etc.) | Total
Programming |  | 2026-08-10 | 2026-08-31 | 21 | 5% | 34500 | 70000 | 35500 | 2.464% |  | 140000 | 70000 | 70000 |  | 18000 | 19000 | 12000 | 0 | 0 | 15000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 70000
Schematic Design |  | 2026-09-01 | 2026-10-16 | 45 | 15% | 120650 | 210000 | 89350 | 8.618% |  | 420000 | 210000 | 210000 |  | 54000 | 57000 | 36000 | 0 | 0 | 45000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 210000
Design Development |  | 2026-10-17 | 2027-01-15 | 90 | 20% | 238100 | 280000 | 41900 | 17.01% |  | 560000 | 280000 | 280000 |  | 72000 | 76000 | 48000 | 0 | 0 | 60000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280000
Construction Documents |  | 2027-01-16 | 2027-05-16 | 120 | 35% | 394050 | 490000 | 95950 | 28.15% |  | 980000 | 490000 | 490000 |  | 126000 | 133000 | 84000 | 0 | 0 | 105000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 490000
Bidding & Negotiations |  | 2027-05-17 | 2027-07-16 | 60 | 5% | 54620 | 70000 | 15380 | 3.901% |  | 140000 | 70000 | 70000 |  | 18000 | 19000 | 12000 | 0 | 0 | 15000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 70000
Construction Administration |  | 2027-07-17 | 2029-01-14 | 547 | 20% | 270100 | 280000 | 9900 | 19.29% |  | 560000 | 280000 | 280000 |  | 72000 | 76000 | 48000 | 0 | 0 | 60000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280000
Warranty |  |  |  | 0 | 0% | 0 | 0 | 0 | 0% | Profit of Grace fee | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Total |  |  |  |  | 100% | 1112020 | 1400000 | 287980 | 79.43% | 20.57% | 2800000 | 1400000 | 1400000 |  | 360000 | 380000 | 240000 | 0 | 0 | 300000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000
Input actual fees negotiated in the yellow cell for each consultant
Department |  |  |  |  | Fee | Cost | Profit | Fee % | Profit %
Architecture / Interiors |  |  |  |  | 1400000 | 1112020 | 287980 | 100% | 100% |  | Add Services | Amount | Detail
Dept Name 2 |  |  |  |  | 0 | 0 | 0 | 0% | 0% |  | Add Svcs #01 | 0
Dept Name 3 |  |  |  |  | 0 | 0 | 0 | 0% | 0% |  | Add Svcs #02 | 0
Mechanical (consultant) |  |  |  |  | 0 | 0 | 0 | 0% | 0% |  | Add Svcs #03 | 0
Misc |  |  |  |  | 0 | 0 | 0 | 0% | 0% |  | Add Svcs #04 | 0
[11 empty] | Add Svcs #05 | 0
Total |  |  |  |  | 1400000 | 1112020 | 287980 | 100% | 100%
Schedule basis
PRINCIPAL IN CHARGE: |  |  |  | Marcus Webb | [6 empty] | Total | 0
INTERIORS: |  |  |  | Miranda G., Grant H.
ARCHITECTURE: |  |  |  | Dana Reyes, Roger S., Sebastian Z., Amy T.
QA/QC Process Information: |  |  |  | QA/QC - Milo
Approval
Architecture / Interiors | Office Manager |  |  | NAME
Dept Name 2 | Office Manager |  |  | NAME
Dept Name 3 | Office Manager |  |  | NAME
Mechanical (consultant) | Office Manager |  |  | NAME
Misc | Office Manager
Formulas:
phase finish = [phase start]+E12
phase start = [phase finish, row above]+1

## PG
Oakhaven Public Safety Campus - GRC-26-0142
Programming
| 3 | Phase Duration in Weeks |  |  | Department % | PHASE FEE | FEE LESS PROFIT | START DATE | COMPLETION DATE | PERSONNEL % OF FEE PER DEPT
| hr/wk | [6 empty] | 2026-08-10 | 2026-08-31
|  | Architecture / Interiors | Hours | Cost | 100% | 70000 | 56000
| 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
Marcus W. | 13.3333 | Principal 2 | 40 | 310 |  | 12400 |  |  |  | 17.71%
| 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
Dana R | 13.3333 | Senior Project Manager | 40 | 175 |  | 7000 |  |  |  | 10%
Roger S | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
| 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
Sebastian Z | 20 | Architect | 60 | 155 |  | 9300 |  |  |  | 13.29%
| 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
Amy T | 0 | Design Professional (Architecture) | 0 | 115 |  | 0 |  |  |  | 0%
| 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
| 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
Miranda G. | 13.3333 | Senior Interior Designer | 40 | 145 |  | 5800 |  |  |  | 8.286%
| 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
| 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
Grant H | 0 | Design Professional (Interiors) | 0 | 100 |  | 0 |  |  |  | 0%
| 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
| 0 | Construction Administration | 0 | 130 |  | 0 |  |  |  | 0%
| 0 | BIM Manager | 0 | 150 |  | 0 |  |  |  | 0%
| 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
William S | 0 | QC Peer Reviewer | 0 | 175 |  | 0 |  |  |  | 0% | Update Cost cell based on Reviewer's Staff Type
| 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 34500 |  |  |  | 49.29%
|  | Dept Name 2 |  |  | 0% | 0 | 0
| 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
| 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
| 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
| 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
| 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
| 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
| 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
| 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
| 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
| 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
| 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
| 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
| 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
| 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
| 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
| 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
| 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
| 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
| 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
| 0 | QC Peer Reviewer |  | 175 |  | 0 |  |  |  | 0% | Update Cost cell based on Reviewer's Staff Type
| 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Dept Name 3 |  |  | 0% | 0 | 0
| 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
| 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
| 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
| 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
| 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
| 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
| 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
| 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
| 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
| 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
| 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
| 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
| 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
| 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
| 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
| 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
| 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
| 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
| 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
| 0 | QC Peer Reviewer |  | 175 |  | 0 |  |  |  | 0% | Update Cost cell based on Reviewer's Staff Type
| 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Mechanical (consultant) |  |  | 0% | 0 | 0
| 0 | Mechanical Engineer |  | 230 |  | 0 |  |  |  | 0%
| 0 | Design Professional (Engineering) |  | 195 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Misc |  |  | 0% | 0 | 0
| 0 |  |  |  |  | 0 |  |  |  | 0%
| 0 |  |  |  |  | 0 |  |  |  | 0%
| 0 |  |  |  |  | 0 |  |  |  | 0%
| 0 |  |  |  |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  |  | 180 |  | 100% | 70000 |  |  |  | 49.29%
0
[5 empty] | TOTALS | 34500 | 56000

## SD
Oakhaven Public Safety Campus - GRC-26-0142
Schematic Design
| 6.4286 |  |  |  | Department % | PHASE FEE | FEE LESS PROFIT | START DATE | COMPLETION DATE | PERSONNEL % OF FEE PER DEPT
| hr/wk | [6 empty] | 2026-09-01 | 2026-10-16
|  | Architecture / Interiors | Hours | Cost | 100% | 210000 | 168000
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
Marcus W. | 12.4444 | Principal 2 | 80 | 310 |  | 24800 |  |  |  | 11.81%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
Dana R | 12.4444 | Senior Project Manager | 80 | 175 |  | 14000 |  |  |  | 6.667%
Roger S | 20.2222 | Senior Architect | 130 | 170 |  | 22100 |  |  |  | 10.52%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
Sebastian Z | 20.2222 | Architect | 130 | 155 |  | 20150 |  |  |  | 9.595%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
Amy T | 28 | Design Professional (Architecture) | 180 | 115 |  | 20700 |  |  |  | 9.857%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
Miranda G. | 12.4444 | Senior Interior Designer | 80 | 145 |  | 11600 |  |  |  | 5.524%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
Grant H | 8.0889 | Design Professional (Interiors) | 52 | 100 |  | 5200 |  |  |  | 2.476%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
William S | 1.8667 | QC Peer Reviewer | 12 | 175 |  | 2100 |  |  |  | 1%
0 | 0 | Administrative | 0 | 80 |  | 0 |  |  |  | 0%
[6 empty] | 120650 |  |  |  | 57.45%
|  | Dept Name 2 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | QC Peer Reviewer |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Dept Name 3 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | QC Peer Reviewer |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Mechanical (consultant) |  |  | 0% | 0 | 0
0 | 0 | Mechanical Engineer |  | 230 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Engineering) |  | 195 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Misc |  |  | 0% | 0 | 0
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  |  | 744 |  | 100% | 210000 |  |  |  | 57.45%
0
[5 empty] | TOTALS | 120650 | 168000

## DD
Oakhaven Public Safety Campus - GRC-26-0142
Design Development
| 12.8571 | Phase Duration in Weeks |  |  | Department % | PHASE FEE | FEE LESS PROFIT | START DATE | COMPLETION DATE | PERSONNEL % OF FEE PER DEPT
| hr/wk | [6 empty] | 2026-10-17 | 2027-01-15
|  | Architecture / Interiors | Hours | Cost | 100% | 280000 | 224000
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
Marcus W. | 3.8889 | Principal 2 | 50 | 310 |  | 15500 |  |  |  | 5.536%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
Dana R | 20.2222 | Senior Project Manager | 260 | 175 |  | 45500 |  |  |  | 16.25%
Roger S | 20.2222 | Senior Architect | 260 | 170 |  | 44200 |  |  |  | 15.79%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
Sebastian Z | 20.2222 | Architect | 260 | 155 |  | 40300 |  |  |  | 14.39%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
Amy T | 27.2222 | Design Professional (Architecture) | 350 | 115 |  | 40250 |  |  |  | 14.37%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
Miranda G. | 12.4444 | Senior Interior Designer | 160 | 145 |  | 23200 |  |  |  | 8.286%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
Grant H | 20.2222 | Design Professional (Interiors) | 260 | 100 |  | 26000 |  |  |  | 9.286%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
William S | 1.4 | QC Peer Reviewer | 18 | 175 |  | 3150 |  |  |  | 1.125%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 238100 |  |  |  | 85.04%
|  | Dept Name 2 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | QC Peer Reviewer |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Dept Name 3 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | QC Peer Reviewer |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Mechanical (consultant) |  |  | 0% | 0 | 0
0 | 0 | Mechanical Engineer |  | 230 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Engineering) |  | 195 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Misc |  |  | 0% | 0 | 0
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  |  | 1618 |  | 100% | 280000 |  |  |  | 85.04%
0
[5 empty] | TOTALS | 238100 | 224000

## CD
Oakhaven Public Safety Campus - GRC-26-0142
Construction Documents
| 17.1429 | Phase Duration in Weeks |  |  | Department % | PHASE FEE | FEE LESS PROFIT | START DATE | COMPLETION DATE | PERSONNEL % OF FEE PER DEPT
| hr/wk | [6 empty] | 2027-01-16 | 2027-05-16
|  | Architecture / Interiors | Hours | Cost | 100% | 490000 | 392000
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
Marcus W. | 2.3333 | Principal 2 | 40 | 310 |  | 12400 |  |  |  | 2.531%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
Dana R | 20.4167 | Senior Project Manager | 350 | 175 |  | 61250 |  |  |  | 12.5%
Roger S | 29.75 | Senior Architect | 510 | 170 |  | 86700 |  |  |  | 17.69%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
Sebastian Z | 26.8333 | Architect | 460 | 155 |  | 71300 |  |  |  | 14.55%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
Amy T | 29.75 | Design Professional (Architecture) | 510 | 115 |  | 58650 |  |  |  | 11.97%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
Miranda G. | 20.4167 | Senior Interior Designer | 350 | 145 |  | 50750 |  |  |  | 10.36%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
Grant H | 26.8333 | Design Professional (Interiors) | 460 | 100 |  | 46000 |  |  |  | 9.388%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
William S | 2.3333 | QC Peer Reviewer | 40 | 175 |  | 7000 |  |  |  | 1.429%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 394050 |  |  |  | 80.42%
|  | Dept Name 2 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | QC Peer Reviewer |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Dept Name 3 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | QC Peer Reviewer |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Mechanical (consultant) |  |  | 0% | 0 | 0
0 | 0 | Mechanical Engineer |  | 230 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Engineering) |  | 195 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Misc |  |  | 0% | 0 | 0
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  |  | 2720 |  | 100% | 490000 |  |  |  | 80.42%
0
[5 empty] | TOTALS | 394050 | 392000

## BN
Oakhaven Public Safety Campus - GRC-26-0142
Bidding & Negotiations
| 8.5714 | Phase Duration in Weeks |  |  | Department % | PHASE FEE | FEE LESS PROFIT | START DATE | COMPLETION DATE | PERSONNEL % OF FEE PER DEPT
| hr/wk | [6 empty] | 2027-05-17 | 2027-07-16
|  | Architecture / Interiors | Hours | Cost | 100% | 70000 | 56000
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
Marcus W. | 0.93333 | Principal 2 | 8 | 310 |  | 2480 |  |  |  | 3.543%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
Dana R | 5.8333 | Senior Project Manager | 50 | 175 |  | 8750 |  |  |  | 12.5%
Roger S | 11.6667 | Senior Architect | 100 | 170 |  | 17000 |  |  |  | 24.29%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
Sebastian Z | 5.8333 | Architect | 50 | 155 |  | 7750 |  |  |  | 11.07%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
Amy T | 5.8333 | Design Professional (Architecture) | 50 | 115 |  | 5750 |  |  |  | 8.214%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
Miranda G. | 5.8333 | Senior Interior Designer | 50 | 145 |  | 7250 |  |  |  | 10.36%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
Grant H | 5.8333 | Design Professional (Interiors) | 50 | 100 |  | 5000 |  |  |  | 7.143%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0.93333 | Administrative | 8 | 80 |  | 640 |  |  |  | 0.9143%
[6 empty] | 54620 |  |  |  | 78.03%
|  | Dept Name 2 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Dept Name 3 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Mechanical (consultant) |  |  | 0% | 0 | 0
0 | 0 | Mechanical Engineer |  | 230 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Engineering) |  | 195 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Misc |  |  | 0% | 0 | 0
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  |  | 366 |  | 100% | 70000 |  |  |  | 78.03%
0
[5 empty] | TOTALS | 54620 | 56000

## CA
Oakhaven Public Safety Campus - GRC-26-0142
Construction Administration
| 78.1429 | Phase Duration in Weeks |  |  | Department % | PHASE FEE | FEE LESS PROFIT | START DATE | COMPLETION DATE | PERSONNEL % OF FEE PER DEPT
| hr/wk | [6 empty] | 2027-07-17 | 2029-01-14
|  | Architecture / Interiors | Hours | Cost | 100% | 280000 | 224000
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
Marcus W. | 0.51188 | Principal 2 | 40 | 310 |  | 12400 |  |  |  | 4.429%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
Dana R | 5.1188 | Senior Project Manager | 400 | 175 |  | 70000 |  |  |  | 25%
Roger S | 5.1188 | Senior Architect | 400 | 170 |  | 68000 |  |  |  | 24.29%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
Sebastian Z | 3.1993 | Architect | 250 | 155 |  | 38750 |  |  |  | 13.84%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
Amy T | 3.1993 | Design Professional (Architecture) | 250 | 115 |  | 28750 |  |  |  | 10.27%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
Miranda G. | 2.5594 | Senior Interior Designer | 200 | 145 |  | 29000 |  |  |  | 10.36%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
Grant H | 2.5594 | Design Professional (Interiors) | 200 | 100 |  | 20000 |  |  |  | 7.143%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0.51188 | Administrative | 40 | 80 |  | 3200 |  |  |  | 1.143%
[6 empty] | 270100 |  |  |  | 96.46%
|  | Dept Name 2 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Dept Name 3 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Mechanical (consultant) |  |  | 0% | 0 | 0
0 | 0 | Mechanical Engineer |  | 230 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Engineering) |  | 195 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Misc |  |  | 0% | 0 | 0
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
0 | 0 |  |  | 0 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  |  | 1780 |  | 100% | 280000 |  |  |  | 96.46%
0
[5 empty] | TOTALS | 270100 | 224000

## Warranty
Oakhaven Public Safety Campus - GRC-26-0142
Warranty
| 0 | Phase Duration in Weeks |  |  | Department % | PHASE FEE | FEE LESS PROFIT | START DATE | COMPLETION DATE | PERSONNEL % OF FEE PER DEPT
| hr/wk | [6 empty] | 0 | 0
|  | Architecture / Interiors | Hours | Cost | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
Marcus W. | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
Dana R | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
Roger S | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
Sebastian Z | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
Amy T | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
Miranda G. | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
Grant H | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Dept Name 2 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Dept Name 3 |  |  | 0% | 0 | 0
0 | 0 | Principal 1 |  | 315 |  | 0 |  |  |  | 0%
0 | 0 | Principal 2 |  | 310 |  | 0 |  |  |  | 0%
0 | 0 | Principal 3 |  | 250 |  | 0 |  |  |  | 0%
0 | 0 | Senior Project Manager |  | 175 |  | 0 |  |  |  | 0%
0 | 0 | Senior Architect |  | 170 |  | 0 |  |  |  | 0%
0 | 0 | Project Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Architect |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Design Professional (Architecture) |  | 140 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Architecture) |  | 115 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Architecture) |  | 65 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer Project Manager |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Senior Interior Designer |  | 145 |  | 0 |  |  |  | 0%
0 | 0 | Interior Project Manager |  | 125 |  | 0 |  |  |  | 0%
0 | 0 | Interior Designer |  | 110 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Interiors) |  | 100 |  | 0 |  |  |  | 0%
0 | 0 | Design Intern (Interiors) |  | 50 |  | 0 |  |  |  | 0%
0 | 0 | Construction Administration |  | 130 |  | 0 |  |  |  | 0%
0 | 0 | BIM Manager |  | 150 |  | 0 |  |  |  | 0%
0 | 0 | Director of VDC |  | 155 |  | 0 |  |  |  | 0%
0 | 0 | Administrative |  | 80 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Mechanical (consultant) |  |  | 0% | 0 | 0
0 | 0 | Mechanical Engineer |  | 230 |  | 0 |  |  |  | 0%
0 | 0 | Design Professional (Engineering) |  | 195 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  | Misc |  |  | 0% | 0 | 0
| 0 |  |  | 0 |  | 0 |  |  |  | 0%
| 0 |  |  | 0 |  | 0 |  |  |  | 0%
| 0 |  |  | 0 |  | 0 |  |  |  | 0%
| 0 |  |  | 0 |  | 0 |  |  |  | 0%
[6 empty] | 0 |  |  |  | 0%
|  |  | 0 |  | 0% | 0 |  |  |  | 0%
0
[5 empty] | TOTALS | 0 | 0