## How to use
How to use this Change Log
1. Open it on the day the project starts, and keep it with the project files.
2. Log every request the day it arrives. Log the ones you approve, the ones you decline, and the ones you only watch.
3. Fill the five core fields every time: Date, Description, Reason, Estimated cost and Impact. Write $0 when there is no fee.
4. Set the Status. Approved means the work goes ahead. Declined means someone decided against it. Watched means nobody has acted on it yet.
5. When a decision is made, write it in Decision and Date closed on the same day, then update the schedule, the fee, the staffing plan and the scope.
6. Tell the team first and the client in the next status update, then mark Team told and Client told.
Before you price any request, run the three checks in order: schedule, coordination, scope. Then ask one question. Did the contract already fund this?
If the contract is unclear rather than silent, take it to the Principal in Charge before you say any number to the client.
Blue text is input. Black text and the totals under each table are fixed.

## Change Log
Change Log
Log every request on the day it arrives, approved, declined or watched. Blue text is input. The # column and the two totals are fixed.
# | Date | Description | Reason, and who raised it | Estimated cost | Impact | Status | Decision | Date closed | Team told | Client told
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
|  |  | Approved fee change | 0
|  |  | Requests logged | 0

## Oakhaven example
Change Log, Oakhaven Public Safety Campus
Worked example from the Oakhaven Risk Register and Change Log (07). Source dates and amounts are from that workbook. Status names follow Module 10.
# | Date | Description | Reason, and who raised it | Estimated cost | Impact | Status | Decision | Date closed | Team told | Client told
1 | 2026-09-18 | Secure evidence storage room in the police wing. Not in the program. | Owner request, raised in a design review. | 12500 | Security consultant added. Layout reworked. | Approved | Amendment 01 approved by the Owner, fee plus $12,500. | 2026-09-28 | Yes | Yes
2 | 2026-11-25 | Two hour separation at the EOC, with added detailing. | Fire Marshal requirement, raised by the AHJ. | 0 | Design change. Inside Basic Services, no fee change. | Approved | Absorbed within the CD scope. No fee change. | 2026-11-27 | Yes | Yes
3 | 2026-12-10 | Possible security vestibule at the public entry. | Owner idea, no request to proceed yet. | 0 | Design effort estimated at $18,000 to $22,000 if authorized. | Watched | Waiting on Owner direction. |  | Yes | No
4 | 2026-12-18 | Value engineering option, alternate roof assembly. | Grace proposal to protect the budget at the CD estimate. | 0 | Cost neutral. No action unless pricing moves. | Watched | Held for the CD estimate. |  | Yes | No
|  |  | Approved fee change | 12500
|  |  | Requests logged | 4
Source: Oakhaven briefing packet, 07_Risk Register & Change Log, entries PCO-001 to PCO-004. PCO-002 and PCO-004 show Potential and Held in the source, and Watched here.