GRACE PM EXCELLENCE ACADEMY · MODULE 12

Phase Debrief

End of each phase. About 20 minutes. Open with the last debrief's actions, then take the five questions in order.

| PROJECT | PHASE | DATE |
| --- | --- | --- |

START HERE   Actions from the last debrief

Ask each owner to show what changed in the work.

| ACTION | OWNER | DATE | WHAT CHANGED IN THE WORK |
| --- | --- | --- | --- |

IN THE ROOM   Records

☐ Phase plan   ☐ Phase numbers from BST   ☐ Change log   ☐ QC Form for the phase

QUESTION 1   What were we trying to do?

Read the success statement and the plan. Agree on the target before you judge the result.

QUESTION 2   What happened?

Walk the records in order: dates, costs, decisions, changes. Facts before causes. Record differences the records don’t settle.

QUESTION 3   What went well, and why?

Name the practice behind the result. Ask what people actually did.

QUESTION 4   What went wrong, and why?

Steps, tools, decisions, time, people, skills. Other views first. What people did and the conditions they faced.

QUESTION 5   What will we do next time?

At least one action. Correct a problem or repeat what worked. Name the owner and set a date.

THE ACTION   One action for the next phase

| ACTION | OWNER | DATE | SENT TO | CHECKED AT |
| --- | --- | --- | --- | --- |