## Sheet1
CONSTRUCTION DOCUMENTS ROADMAP
PROJECT NAME
PROJECT NO. |  |  |  |  | PIC:
DATE |  |  |  |  | PM:
PA/AC:
INSTRUCTION NOTES
1. Refer to Responsibility Key below. Team shall assign responsibilities for tasks listed below.
2. Tasks listed below are not necessarily in cronological order in which they need to be performed/completed.
3. Not all tasks are applicable. If not applicable to project or phase, denote in Remark Column.
4. Enter date that the task is completed.
5. Person responsible shall initial task, confirming that task has been completed.
6. CD's shall be issued as "FOR CONSTRUCTION" to the General Contractor and local jurisdiction for Permit Review. No drawings shall be designated "FOR PERMIT". Any changes deriving out of City/State review comments shall be issued as an addendum or ASI to the Construction Documents.
RESPONSIBILITY KEY
1:Primary Responsibility 2:Secondary Responsibility 3:Support
TASK | PIC | PM | PA | OTHER | DATE COMPLETE | INTL. | REMARK/REFERENCE
Review / Revise Code Analysis
CD Minimum Drawings Requirements
Coordinate Drawings with All Disciplines
QC Drawings
Verify / Distinguish Between OFOI, OFCI & CFCI
Update / Finalize Specifications
Acquire TDLR Registration No.
Submittals to Governing Agencies
Transmit Drawings to GC & to Jurisdiction for Permit Review
Obtain Owner Sign-Off of CD Drawings and Approval to Proceed to construction
Review unresolved issues on the Design Development checklist.
Periodically review internal office budgets and production schedules; compare with actual progress.
Review and update schedule of completion dates for this and all subsequent phases. Inform the project team and owner of any revisions.
Review and update staff time and production cost projections.
Adjust number and type of staff as required.
Distribute updated project schedule to Owner, project staff and consultants if required.
As documents develop, confer with and obtain further review from regulatory agencies such as:
Building Department
Fire Marshal (State and Local)
Dept. of Health
Dept. of Education
Other:
Check with the applicable regulatory agencies and establish schedule for submission and/or review.
Coordinate the work of all team members, including consultants.
Coordinate drawings with Project Manual.
Update preliminary construction cost estimate and advise the Owner of any revisions, scope creep.
Review the program and verify compliance.
Re-check Design Development documents for code compliance.
Develop a list of required drawings; check requirements of the Owner and governing bodies.
Prepare a mock-up list of all project drawing sheets; their sequence, and the information to appear on each sheet. Distribute copies to concerned parties for review, then distribute final copies to all staff as a supervisory guide. | [6 empty] | Refer to Forms Folder
Complete project manual specifications and front end.
Review the completed working drawing index with all concerned parties. Obtain feedback and make revisions as necessary.
Determine the completion date of the limited architectural floor plan base sheet(s) for consultants’ use.
Develop title block format (check requirements of owner licensing laws and governing bodies). Use legal names of all entities.
Develop format for door, window and finish schedules.
Establish a checklist and timetable for the client’s applications for approvals and permits for governing bodies.
If applicable, determine alternates, cash allowances and unit prices.
Obtain Owner’s instructions on insurance, bonds, construction agreements and bidding procedures.
Review of front end submitted at Design Development phase.
Determine what items, if any, are to be furnished by the Owner, and those items not to be included in the contract.
Verify Owner’s acceptance of the proposed designs for mechanical and electrical systems.
Monitor approval and permit process.
Obtain schedule for delivery and installation of Owner-furnished materials.
Assemble final drawings and specifications for coordination.
Conduct team meetings to resolve coordination issues.
Revise documents as required.
If project will be bid, assemble bidding documents.
Determine whether prevailing wage rate statuses apply in project jurisdiction.
Prepare final calculations of net and gross areas and volumes.
Obtain each consultant’s final construction cost estimate for their portion of the project.
Prepare final construction cost estimate.
Prepare testing and quality control program budgets and assist Owner in selection of testing agency.
Check PDF plans and project manual against index and for problems with PDF’s.
Compile consultants drawing and specifications, incorporate into bid documents.
Submit drawings, Project Manual, construction cost estimate and area calculation to the Owner.
Review list of potential bidder with the Owner for private jobs.
Obtain and review qualification statements from interested bidders.
Place Architect’s and engineers’ seals on the documents and obtain signatures required by reviewing authorities.
Assist Owner in filing documents for final approvals and permits.
Obtain Owner’s written authorization to proceed to the Bidding or Negotiation phase.
Prepare estimate of probable construction cost based on all available data. Include appropriate contingency to cover future development of the project. If requested by Owner, provide a detailed estimate and/or life cycle costing as additional service.
Submit Construction Documents to the Owner. (These documents may include, but may not be limited to, drawings, descriptions, calculations, outline specifications, colors, materials and statements of probable construction cost. Verify exact documents required in Owner/Architect contract.
Plan appropriate presentation media, optional design features if necessary
Review meeting with Owner at the BIM Lab
Obtain Owner’s written approval of Construction Documents, and direction to proceed into Construction Administration.
Notify accounting of phase change.