## Sheet1
DESIGN DEVELOPMENT QC CHECKLIST
PROJECT NAME
PROJECT NO. | PIC:
DATE | PM:
PA/AC:
INSTRUCTION NOTES
1. The following list outlines the minimum requirements established for all projects.
2. All criteria listed below shall be identified and coordinated on drawings as applicable prior to submitting for Quality Control Review.
3. The Project Architect / Project Coordinator is responsible for ensuring that the listed criteria is performed and adhered to by signing off on task.
4. PA shall establish any additional requirements needed with the Project Manager or Principal in Charge.
5. Refer to Grace Standards/Instructions for Drawing Set Up Requirements
RESPONSIBILITY KEY
1:Primary Responsibility 2:Secondary Responsibility 3:Support
TASK | DATE COMPLETE | SIGN OFF
COVER SHEET
List Code References and Dates Correctly. Verify with Governing Agencies
Construction Type is referenced per Building Code Analysis
Occupancy Type is referenced per Code Analysis
Confirm Project Team Names, Titles, Addresses and Phone Numbers are corect and match Project Directory
Confirm Consultant Sheet Listing and Titles
Confirm that General Notes Apply and Edit as Required for Specific Project
Provide Vicinity Map to Accurately Locate the Project; Provide True North Indicator
SITE PLAN
General Notes are Applicable and Accurate; Confirm there are no contradictions with Consultant Drawings
Legends provided as required and accurate
Coordinate Architecural Site Plan with Civil Drawings:
Identify and Indicate Property Dimensions / Information / Setbacks / Easments
Provide Dimensional Control to Tie Down Building and Parking to Site
Confirm with Client if any Deed Restrictions exist for the Site
Research Parking Ordinances for Off-Street Parking and Loading Requirements
Research Sign Ordinance for Project Monument Signs
Confirm Building Setbacks are Met
Deternine Finished Floor Elevation with Civl
Review Site Accessibility; Curb Ramps, Slopes, Rails, Signs, etc. Identified
Building Utility Outflow Lines are coordinated with Civil Site Utility Lines for Size and Locations
If Gutter Downspouts Tie Into Sub-surface Drainage, Coordinate Locations with MEP and Civil
Provide Details Required for Enclosures, Signs, Flagpoles, Fountains, etc.; Locate all on Site Plan
Ensure that Enclosure Dimensions are Adequate for Equipment Requirements
Ensure that Enclosure Materials are Acceptable per Local Ordinances
Identify which Items are Owner Furnished and Installed vs. Contractor Furnished and Installed
Meter Sizes Identified on Civil for Domestic, Fire and Irrigation Lines? Verify with Civil and Local Municipality
Verify Fire Lane Requirements ; Coordinate with Civil
Fire Lane Configuration
Fire Lane Striping
Minimum Turning Radius
Coordinate Tree Mitigation with Landscaping if Required
Coordinate Location of Landscape Irrigation Control Panel
Verify that Landscape Drawings Locate Sleeves Under Sidewalks and Paved Areas
LIFE SAFETY PLANS
Floor Plan is Sub-divided in Quadrants as Required Based on Size of Footprint. Match A2 Series Plans.
Multiple Floor Plans Provided for Multi-story Building. Match A2 Series Plans.
Identify Smoke Compartments
Define exit travel path distances to not exceed code requirements
Provide Exit Calculation for each Smoke Compartment
Identify all Rated Fire and Smoke Walls; Provide Legend for Wall Types
Locate Fire Extinguishers on Plan
Locate exit signage with Directional Arrows as Needed - Provide locations to MEP consultant
Locate Fire Alarm Annunciator Panel (FAAP) on Plan
List Correct Code References and Dates; Match Cover Sheet
FLOOR PLAN
Ensure Consultants Have Current Backgrounds
Key in Basic Partition Types on plan(s)
Dimensions
Interior – Critical Room Dimensions
Corridor Clear Widths
Key in Elevation Markers – Interior & Exterior
Wall Section Markers
Details are keyed into wall sections appropiately
Room Names & Numbers are identified properly
Verify line types and weights are correct and consistent
Verify that plumbing walls are dimensioned properly for scheduled plumbing
Verify that sheet match lines are correctly drawn and labeled (if applicable)
Provide key plan as applicable for multi-floor or multi- tenant spaces
Make Sure General Notes Apply; Don't Just Copy Over From Another Project
Indicate Grommets on Countertops if You Want to Contol Where They Are Located
Indicate FRT Plywood Sheets on Walls in IT and Electrical Closets (Paint to Match Walls)
Ensure Corridor Widths and Door Openings Allow for Movement of Major Equipment
If Rated Wall Construction at Structural Columns Cannot be Shown Adequately, Provide Enlarged Detail
Show All Patient Toilet Room Doors to Swing Out
Key In Glass/Window Types to Coordinate with Frame and Glass Types on A5 Series Drawings
ROOF PLANS
Basic Roof Design w/ Peaks, Valleys, Gutters and Drains
(Show MEP Equipment if available)
Indicate Roof Slopes
Describe Roofing Systems; Legend
Locate Ladders if Applicable
Show Parapet Coping
Locate Roof Access
Locate Walkway Protection Paths
Locate Equipment Screening if Applicable
Provide Cut Sheets of Roofing Components and Place in Project File
Key in Wall Section Markers
Make Sure General Notes Apply; Don't Just Copy Over From Another Project
ENLARGED PLANS
Develop enlarged plan from overall floorplan to adequately deliniate areas requiring more detail
Show as much detail as posible and include notes and keyed references to other details as required
REFLECTED CEILING PLANS
Verify ceiling plans match architectural backgrounds
Verify that MEP Consultant backgrounds match architectural
Verify that all lighting fixtures are coordinated with Electrical Lighting drawings
Verify that all HVAC supply and return diffusers are coordinated with HVAC drawings
Verify duct sizes and routing do not interfere with ceiling fixtures and structural beams (adequate plenum depth)
Verify that Architectural General Notes do not conflict with Consultant notes
Notes and detail references are properly keyed
Ceiling mounted equipment and special ceiling treatments are properly identified and coordinated with consultants
TYPICAL PARTITION SHEET
Use standard Grace partition sheet
Modify sheet details, partition types and notes as applicable to project
EXTERIOR ELEVATIONS
Texture differing materials
Locate all Wall Sections
Show elevation heights; Ground floor elevation shall be designated as Finish Floor EL.= 100'-0"
Finish grade line is different than finish floor line. Delineate as such.
Locate Typical Wall Sections
WALL SECTIONS
Typical Wall Sections to best describe building requirements
Show basic structural systems
Call out materials & systems
Key to details
PLAN & SECTION DETAILS
Develop plan and section details as needed per job specifics
Detail all non-typical conditions.
STAIRS AND ELEVATORS
Develop enlarged plans to deliniate in more detail
Develop stair and elevator sections; Key sections on enlarged plans
Develop details and key them to plan and sections
Coordinate structural openings and framing for stair and elevator openings with structural engineer
Coordinate venting and pressurization requirements of elevator shafts with MEP consultant
INTERIOR ELEVATIONS
Show basic cabinet/casework elevations with dimensions, equipment, U/C lights and electrical outlets shown
Coordinate knee space locations and show on plans
Show all owner furnished FF&E as dashed lines.